## Product backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Intoduction to the Project -Detailed | MUST HAVE | N/A | Dinesh Kumar | 3- Completed
S1 | S1 | US-002 | Project's Workflow Discussed | MUST HAVE | Lucid chart | Dinesh Kumar | 3- Completed
S1 | S1 | US-003 | Project Documentation Discussion (Agile document) | MUST HAVE | N/A | Dinesh Kumar | 3- Completed
S2 | S2 | US-004 | Data Aquisition via Api | MUST HAVE | Flask | Dinesh Kumar | 3- Completed
S2 | S2 | US-005 | Data Aquisition via Web scraping | SHOULD HAVE | Beautifulsoup | Dinesh Kumar | 3- Completed
S2 | S2 | US-006 | Collection of Dataset | MUST HAVE | Kaggle | Dinesh Kumar | 3- Completed
S3 | S3 | US-007 | Oauth Framewok integration | COULD HAVE | Google Oauth | Dinesh Kumar | 3- Completed
S3 | S3 | US-008 | Database integration - Uploading Datasets | MUST HAVE | MongoDB | Dinesh Kumar | 3- Completed
S4 | S4 | US-009 | OCR Integration and discussion | MUST HAVE | Tesseract | Dinesh Kumar | 3- Completed
S4 | S4 | US-010 | Pre-processing the dataset (images) | MUST HAVE | Pytesseract | Dinesh Kumar | 3- Completed
S4 | S4 | US-011 | Integration of Post processing techniques | MUST HAVE | Regex | Dinesh Kumar | 3- Completed
S5 | S5 | US-012 | Visualization of processed data | MUST HAVE | Matplotlib | Dinesh Kumar | 3- Completed
S6 | S6 | US-013 | LLM model integration | MUST HAVE | PyTorch | Dinesh Kumar | 3- Completed
S6 | S6 | US-014 | Model Training - with dataset | MUST HAVE | Sklearn | Dinesh Kumar | 3- Completed
S7 | S7 | US-015 | Final Code Compilation: Ensuring Seamless Integration | MUST HAVE | VsCode | Dinesh Kumar | 3- Completed
S8 | S8 | US-016 | Testing and Deployment | MUST HAVE | HTML | Dinesh Kumar | 3- Completed

## Sprint backlog
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 71 | 30 | 20 | 12 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US-001 | TID-01 | Intoduction to the Project -Detailed | 2024-12-04 | 2024-12-06 | Dinesh Kumar | Others | 3- Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-002 | TID-02 | Project's Workflow Discussed | 2024-12-07 | 2024-12-08 | Dinesh Kumar | Design | 3- Completed | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-003 | TID-03 | Project Documentation Discussion (Agile document) | 2024-12-08 | 2024-12-08 | Dinesh Kumar | Others | 3- Completed | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-004 | TID-04 | Data Aquisition via Api | 2024-12-17 | 2024-12-20 | Dinesh Kumar | Coding | 3- Completed | 4 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-005 | TID-05 | Data Aquisition via Web scraping | 2024-12-17 | 2024-12-20 | Dinesh Kumar | Coding | 3- Completed | 5 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-006 | TID-06 | Collection of Dataset | 2024-12-21 | 2024-12-24 | Dinesh Kumar | Coding | 3- Completed | 4 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-007 | TID-07 | Oauth Framewok integration | 2024-12-26 | 2025-01-27 | Dinesh Kumar | Coding | 3- Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-008 | TID-08 | Database integration - Uploading Datasets | 2025-01-28 | 2024-12-30 | Dinesh Kumar | Coding | 3- Completed | 4 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-009 | TID-09 | OCR Integration and discussion | 2025-01-01 | 2025-01-05 | Dinesh Kumar | Coding | 3- Completed | 5 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-010 | TID-10 | Pre-processing the dataset (images) | 2025-01-07 | 2025-01-08 | Dinesh Kumar | Coding | 3- Completed | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-011 | TID-11 | Integration of Post processing techniques | 2025-01-10 | 2025-01-13 | Dinesh Kumar | Coding | 3- Completed | 5 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-012 | TID-12 | Visualization of processed data | 2025-01-14 | 2025-01-15 | Dinesh Kumar | Coding | 3- Completed | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-013 | TID-13 | LLM model integration | 2025-01-16 | 2025-01-17 | Dinesh Kumar | Coding | 3- Completed | 4 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-014 | TID-14 | Model Training - with dataset | 2025-01-17 | 2025-01-20 | Dinesh Kumar | Coding | 3- Completed | 10 | 3 | 3 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-015 | TID-15 | Final Code Compilation: Ensuring Seamless Integration | 2025-01-20 | 2025-01-24 | Dinesh Kumar | Integration Test | 3- Completed | 8 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US-016 | TID-16 | Testing and Deployment | 2025-01-25 | 2025-01-27 | Dinesh Kumar | System Test | 3- Completed | 7 | 3 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Standup meeting
Sprint | Day | Impediments | Action Taken
S1 | Day 3 | Unclear Workflow Processes and steps | Conducted meeting to define and document clear workflow processes
S2 | Day 17 | Difficulty in data acquition via Bank API due to policy restrictions, etc. | Adhering to the bank policy extractd data which is easily available
S3 | Day 35 | Lack of accuracy with OCR | Implemented additional preprocessing techniques to enhance OCR accuracy
S6 | Day 46 | Challenges with LLM model | Collaborated with mentor to optimize and troubleshoot the LLM model
S6 | Day 46 | Difficulty in fine-tuning te model | Utilized distiled version of models available free of cost to improve model performance.
S7 | Day 50 | Difficulty in integrating the codes | Conducted code review sessions to ensure seamless integration
S8 | Day 55 | Error and bugs faced during the deployment of app in cloud | Testing and monitoring to identify and resolve deployment issues.